## Slide 1
DATA COMMITTEE MEETING 5.28.2021
Notes: Justice Earls

## Slide 2
TREC Survey and Model Policy Project
Notes: NCCJ

## Slide 3
Project Outline
Survey Development | Send Survey | Follow-up with Calls and Emails |  |  | REPEAT
 |  | Model Policy Development | Publish Model Policies | Targeted Outreach and Technical Assistance | 

## Slide 4
Survey Development – Law Enforcement
 | LAW ENFORCEMENT
TF Staff | Natalia Botella, Allyson Barkley
Survey Drafting Group | Sergeant Garten, Chief Smythe
Topics/Policy to be Surveyed | MODEL POLICY Traffic Stops Citations and summons Consent Searches Protest Response Use of Force BEST PRACTICE Pre-arrest Diversion

## Slide 5
Survey Development – Prosecutors
 | PROSECUTORS
TF Staff | Jasmine McGhee, Ellen Spolar
Survey Drafting Group | Jeff Welty, Mary Pollard, Boz Zellinger
Topics/Policy to be Surveyed | MODEL POLICY De-prioritization of Low Level Offenses: Marijuana / Traffic Offenses / Class 3 Misdemeanors Dismissal of Criminal Justice Debt / Mass Amnesty Guide Overall Prosecutor Guide Habitual Felony Officer Involved Use of Force Minimum Age of Prosecution School-based Referrals Ability to Pay Advanced Supervised Release BEST PRACTICE Progress on / Willingness to Collect and Use Data Post-arrest Diversion

## Slide 6
Send Surveys - Timeline
May 2021
Friday, May 21: Finalize assignment of drafting teams
Wednesday, May 26: Staff complete draft of survey questions; Send to Drafting Team for review prior to meeting
Friday, May 28: Drafting teams to hold meeting / exchange emails on first draft of survey questions
Friday, May 28: Finalize list generation

## Slide 7
Send Surveys and Follow up - Timeline
June 2021
Friday, June 4: Drafting teams to submit final draft survey questions
Monday, June 7: Co-Chairs sent surveys for final review
Monday, June 14: Send combined survey to all respondents with deadline of Friday, June 25
Monday, June 28: Staff to pull of survey data results to determine assignments for summer interns to make calls to outstanding respondents over the next three weeks
July 2021
Monday, July 12: Send final follow-up survey to outstanding agencies/actors

## Slide 8
Next Steps
June-August 2021
Develop model policies
Create strategies/find resources for technical assistance to agencies/actors that express interest in TREC-recommended policies and programs.
Please reach out to me if you would like to be involved in the Model Policy drafting project

## Slide 9
TREC Study Solicitation
Notes: NCCJ

## Slide 10
Study solicitation
Collaboration with Governor’s Office of Strategic Partnerships was released to OSP’s researcher list serve to start receiving applications on May 12th.
Rec 30: Commission a study on racial disparities in how protests and demonstrations are policed in North Carolina
Rec 124: Study Of Race Measures
To send again next week; please forward to your contacts.