## trec-implementation
TREC Implementation
ncdoj.gov/trec
C#1: Executive Committee
Name | Deliverables | Deliverable Status | Buckets | Solution Section | Check Back In | Resources Needed | Cost | Committee | Issue | Status
Rec #2: Add crisis intervention training for current law enforcement officers | Define baseline knowledge (including physical component) that every officer needs |  | Training | Reimagine public safety and reinvest in communities |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Define baseline knowledge (including physical component) that every officer needs
Rec #7: Train law enforcement agency heads on community policing | Connect with Eddie Caldwell about Sheriffs' Association implementing this training | Working on it | Training | Train law enforcement to promote public safety and get community support |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Connect with Eddie Caldwell about Sheriffs' Association implementing this training | Jasmine McGhee | Working on it
Rec #17: Treat addiction as a public health crisis, including substance use addictions that disproportionately impact Black and brown communities, such as crack cocaine. | Draft language on race and ethnicity requirements for proposed drug treatment courts, Facilitate Learning Series panel on substance use | Working on it | Policy | Promote diversion and other alternatives to arrest |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Draft language on race and ethnicity requirements for proposed drug treatment courts | Ellen Spolar
| Facilitate Learning Series panel on substance use |  | Working on it
Rec #22: Train all public school employees and SROs on the proper role of SROs | Work with DPI to draft survey for SROs, Schedule meetings with school boards, superintendents, and school board attorneys, Analyze current SRO-related trainings, Draft proposed training plan for NCJA implementation, Research and draft memo on rights of students, Have DHHS, Center for Safer Schools, and NCJA sign off on survey, Send survey and analyze responses | Done, Working on it, Working on it, Working on it, Done, Working on it | Training, SROs | Revise the role of School Resource Officers |  |  |  | C1:Exec | Yes | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Work with DPI to draft survey for SROs | Jasmine McGhee | Done
| Schedule meetings with school boards, superintendents, and school board attorneys | Jasmine McGhee | Working on it
| Analyze current SRO-related trainings | Jasmine McGhee | Working on it
| Draft proposed training plan for NCJA implementation | Jasmine McGhee
| Research and draft memo on rights of students | Jasmine McGhee | Working on it
| Have DHHS, Center for Safer Schools, and NCJA sign off on survey |  | Done
| Send survey and analyze responses |  | Working on it
Rec #25: Support Task Force on Safer Schools State Action Plan |  |  | Policy, SROs | Revise the role of School Resource Officers | 2021-08-03 |  |  | C1:Exec | NO | On hold
Rec #27: Adopt a mandatory statewide policy on law enforcement facilitation of peaceful demonstrations | Define OIUFI, Gather bullets for peaceful protests, Research and draft memo for Commissions, Draft presentation for Commissions | Comm Input Needed, Working on it, Done, Done | Commissions | Peacefully facilitate protests and demonstrations |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Define OIUFI | Jasmine McGhee | Comm Input Needed |  |  | 2021-03-09 | 2021-03-26
| Gather bullets for peaceful protests |  | Working on it
| Research and draft memo for Commissions |  | Done
| Draft presentation for Commissions |  | Done
Rec #28: Create and update protest guidelines to consider best practices and First Amendment concerns | Collect sample policies across agencies, Identify missing concepts in sample policies and gather most important concepts from across agencies, Check CALEA guidelines, Confirm where NCLEA is on this as part of statewide accreditation | Done | Commissions | Peacefully facilitate protests and demonstrations |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Collect sample policies across agencies | Leslie Dismukes | Done
| Identify missing concepts in sample policies and gather most important concepts from across agencies | Leslie Dismukes
| Check CALEA guidelines | Leslie Dismukes
| Confirm where NCLEA is on this as part of statewide accreditation | Leslie Dismukes
Rec #29: Review and update protest and demonstration training | Investigate whether the Sheriffs' Association achieves this recommendation, Draft new training plan | Done, Working on it | Training | Peacefully facilitate protests and demonstrations |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Investigate whether the Sheriffs' Association achieves this recommendation | Leslie Dismukes | Done
| Draft new training plan |  | Working on it
Rec #34: Establish early intervention systems for officers repeatedly violating use of force policies | Legislative Comm handling | Working on it | Policy | Revise use of force policies |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Legislative Comm handling |  | Working on it |  | C3:Leg | 2021-03-12 | 2021-03-24
Rec #40: Revise standards to require that officers not engage in excessive or unjustified use of force or abuse the power of the position | Research and draft memo on standards and possible revisions, Draft presentation for Commissions | Done, Done | Commissions | Improve law enforcement accountability and culture |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research and draft memo on standards and possible revisions | Leslie Dismukes | Done
| Draft presentation for Commissions | Leslie Dismukes | Done
Rec #41: Expand authority to allow for suspension, revocation, or denial of certification based upon an officer’s excessive use of force or abuse of power | Research and draft memo on current standards and possible revisions, Draft presentation for Commissions | Done, Done | Commissions | Improve law enforcement accountability and culture |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research and draft memo on current standards and possible revisions | Leslie Dismukes | Done
| Draft presentation for Commissions | Leslie Dismukes | Done
Rec #42: Require notification by both the officer and the agency for specific use of force incidents | Research and draft memo on current standards and possible revisions, Draft presentation for Commissions | Done, Done | Commissions | Improve law enforcement accountability and culture |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research and draft memo on current standards and possible revisions | Leslie Dismukes | Done
| Draft presentation for Commissions | Leslie Dismukes | Done
Rec #43: Increase transparency about officer discipline and decertification through a publicly available databse | Research and draft memo on current practices and possible revisions, Draft presentation for Commissions | Done, Done | Commissions | Improve law enforcement accountability and culture |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research and draft memo on current practices and possible revisions | Leslie Dismukes | Done
| Draft presentation for Commissions | Leslie Dismukes | Done
Rec #44: Support psychological screenings for all law enforcement officers | Research and draft memo on current practices and possible revisions, Draft presentation for Commissions | Done, Done | Commissions | Improve law enforcement accountability and culture |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research and draft memo on current practices and possible revisions | Leslie Dismukes | Done
| Draft presentation for Commissions | Leslie Dismukes | Done
Rec #45: Repeat pscyhological evaluations either after a certain number of years of service or before promotion | Research and draft memo on current practices and possible revisions, Draft presentation for Commissions | Done, Done | Commissions | Improve law enforcement accountability and culture |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research and draft memo on current practices and possible revisions | Leslie Dismukes | Done
| Draft presentation for Commissions | Leslie Dismukes | Done
Rec #46: Strengthen the ongoing development of a statewide law enforcement accreditation program | Research and draft memo for Commissions, Draft presentation for Commissions | Done, Done | Commissions | Improve law enforcement accountability and culture |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research and draft memo for Commissions |  | Done
| Draft presentation for Commissions |  | Done
Rec #51: Develop and disseminate best practices guide for recruitment and retention | Draft plan for Commissions consideration | Done | Commissions | Recruit and retain a racially equitable work force |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Draft plan for Commissions consideration | Leslie Dismukes | Done
Rec #54: Ensure the North Carolina Administrative Code provisions regarding Minimum Standards and Revocation, Denial, and Decertification are the same for both Commissions | Research and draft memo for Commissions, Draft presentation for Commissions | Done, Done | Commissions | Recruit and retain a racially equitable work force |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research and draft memo for Commissions |  | Done
| Draft presentation for Commissions |  | Done
Rec #55: Require law enforcement agencies of a certain size to create a diversity task force | Research and draft memo on current practices and possible revisions, Draft proposal for NCLEA | Done, Working on it | Commissions | Recruit and retain a racially equitable work force |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research and draft memo on current practices and possible revisions | Leslie Dismukes | Done
| Draft proposal for NCLEA | Leslie Dismukes | Working on it
Rec #56: Revamp basic enforcement training |  |  | Training | Train law enforcement to promote public safety and get community support |  |  |  | C1:Exec | NO | Working on it
Rec #57: Revamp in-service training | Review lesson plans from larger LEAs and select trainings to add/adapt for smaller LEAs, Investigate legal implications of sharing best practice lesson plans across agencies |  | Training | Train law enforcement to promote public safety and get community support |  |  |  |  | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Review lesson plans from larger LEAs and select trainings to add/adapt for smaller LEAs | Jasmine McGhee
| Investigate legal implications of sharing best practice lesson plans across agencies | Leslie Dismukes
Rec #58: Require trainings on internal law enforcement agency policies | Contact Chief H as the chair of the NCLEA Working Group to ask that this be an accreditation pillar, Research possible legislative models | Done | Training | Train law enforcement to promote public safety and get community support |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Contact Chief H as the chair of the NCLEA Working Group to ask that this be an accreditation pillar | Jasmine McGhee | Done
Research possible legislative models
Rec #64: Screen incarcerated individuals for victimization and provide appropriate services | GCC Funding Priority, Analyze DPS Prisons report |  | Prisons | Support restorative justice initiatives and victim equity | 2021-08-10 |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| GCC Funding Priority | Natalia Botella
Analyze DPS Prisons report
Rec #70: Establish a juvenile review board within the Governor’s Clemency Office |  |  | Clemency | Stem the school to prison pipeline and rethink juvenile justice | 2021-04-29 10:32 |  |  | C1:Exec | NO | Done
Rec #85: Require implicit bias and racial equity training for parole staff | Analyze DPS Prisons report |  | Training, Prisons | Implement racial equity training for court system actors | 2021-08-10 |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Analyze DPS Prisons report
Re #86: Require racial equity and victim services training for Victim Compensation Fund employees and members |  |  | Training, Policy | Implement racial equity training for court system actors |  |  |  | C1:Exec | NO | Working on it
Rec #95: Increase funding for Governor’s Clemency Office and Parole Commission |  |  | Clemency | Reduce current sentencing and incarceration disparities |  |  |  | C1:Exec | NO | Working on it
Rec #96: Increase NCDPS flexibility on incarcerated individuals’ release dates | Analyze DPS Prisons report |  | Prisons | Reduce current sentencing and incarceration disparities | 2021-08-10 |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Analyze DPS Prisons report
Rec #105: Transform the use of restrictive housing | Review data on current access to programming and determine areas for improvement, Analyze DPS Prisons report |  | Prisons | Amend incarceration facilities’ practices and programming and address prison discipline | 2021-08-10 |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Review data on current access to programming and determine areas for improvement
Analyze DPS Prisons report
Rec #106: Protect pregnant people in jails and prisons | Look into models for legislative change, Analyze DPS Prisons report, Write memo comparing against Dignity Act |  | Prisons | Amend incarceration facilities’ practices and programming and address prison discipline | 2021-08-10 |  |  |  | NO
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Look into models for legislative change
Analyze DPS Prisons report
Write memo comparing against Dignity Act
Rec #107: Enhance prison personnel | Analyze DPS Prisons report |  | Prisons | Amend incarceration facilities’ practices and programming and address prison discipline | 2021-08-10 |  |  |  | NO
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Analyze DPS Prisons report
Rec #108: Increase funding for mental health services and programs in prisons | Review data on current access to programming and determine areas for improvement, GCC funding pitch, Analyze DPS Prisons report |  | Prisons | Amend incarceration facilities’ practices and programming and address prison discipline | 2021-08-10 |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Review data on current access to programming and determine areas for improvement
| GCC funding pitch | Natalia Botella
Analyze DPS Prisons report
Rec #109: Increase due process protections for people accused of disciplinary offenses | Analyze DPS Prisons report |  | Prisons | Amend incarceration facilities’ practices and programming and address prison discipline | 2021-08-10 |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Analyze DPS Prisons report
Rec #110: Expand use of restorative justice and rehabilitation programming | Review data on current access to programming and determine areas for improvement, GCC funding pitch, Analyze DPS Prisons report |  | Prisons | Amend incarceration facilities’ practices and programming and address prison discipline | 2021-08-10 |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Review data on current access to programming and determine areas for improvement
| GCC funding pitch | Natalia Botella
Analyze DPS Prisons report
Rec #123: Support the Statewide Reentry Council Collaborative’s recommendations | GCC Funding pitch, Analyze DPS Prisons report |  | Prisons | Reduce collateral consequences of criminal convictions | 2021-08-10 |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| GCC Funding pitch | Natalia Botella
Analyze DPS Prisons report
2021-04-29 to 2021-08-10
C#2 Judicial Committee
Name | Deliverables | Deliverable Status | Buckets | Solution Section | Check Back In | Resources Needed | Cost | Committee | Issue | Status
Rec #24: Encourage School Justice Partnerships to reduce students’ juvenile court involvement | Draft statement to send to Justice Newby, Determine # of existing and active SJPs, Identify possible LE partners, Conversation with Judges and Judge Corpening concerning outreach to Justice Newby and LE, Identify best practices for data collection in other states, Organize listening sessions with key stakeholders, Organize public event spotlighting SJPS in conjunction with back to school, Connect with ACES Task Force for collaboration | Done, Done, Working on it, Done, Working on it, Working on it | AOC | Revise the role of School Resource Officers |  |  |  | C2:Judicial | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Draft statement to send to Justice Newby | Samuel Davis | Done
| Determine # of existing and active SJPs | Samuel Davis | Done
| Identify possible LE partners | Samuel Davis | Working on it
| Conversation with Judges and Judge Corpening concerning outreach to Justice Newby and LE | Samuel Davis, Allyson Barkley | Done
| Identify best practices for data collection in other states | Samuel Davis | Working on it
Organize listening sessions with key stakeholders
Organize public event spotlighting SJPS in conjunction with back to school
| Connect with ACES Task Force for collaboration | Samuel Davis | Working on it
Rec #84: Require racial equity training for court system personnel, including judges, DAs, and public defenders | Contact US reps/senators for resources/data, Set up call with Vera Institute and CoDA to discuss training partnership | Done, Working on it | AOC | Implement racial equity training for court system actors |  |  |  | C2:Judicial | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Contact US reps/senators for resources/data |  | Done
| Set up call with Vera Institute and CoDA to discuss training partnership | Jasmine McGhee | Working on it | 2021-07-06
Rec #87: Educate prosecutors, their staff, and officers of justice on unconscious bias in the criminal justice process and prosecutorial decision-making | Research AOC ability to mandate training, Develop list of DAs to contact for input and support on various prosecutorial recs, Schedule meeting with CoDA for mid-May | Done, Working on it, Done | Conference of DAs | Promote racially equitable prosecutorial practices |  |  |  | C2:Judicial | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research AOC ability to mandate training | Allyson Barkley | Done
| Develop list of DAs to contact for input and support on various prosecutorial recs |  | Working on it
| Schedule meeting with CoDA for mid-May |  | Done
Rec #89: Study and adopt evidence-based reforms for reducing and eventually eliminating racial disparities in charging decisions and prosecutorial outcomes | Schedule meeting with CoDA for mid-May, Set up call with Wilson Center and CoDA to discuss potential partnership, Send CoDA final survey draft | Done, Working on it, Done | Conference of DAs | Promote racially equitable prosecutorial practices |  |  |  | C2:Judicial | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Schedule meeting with CoDA for mid-May |  | Done
| Set up call with Wilson Center and CoDA to discuss potential partnership | Jasmine McGhee | Working on it
| Send CoDA final survey draft |  | Done
Rec #90: Establish working groups led by district attorneys to review and approve every habitual felony charging decision | Conversation with Lorin Freeman and CoDAs about progress on model to be applied across NC, Schedule meeting with CoDA, Send CoDA final survey draft, Develop list of districts to partner with on implementation | Working on it, Done, Done | Conference of DAs | Promote racially equitable prosecutorial practices |  |  |  | C2:Judicial | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Conversation with Lorin Freeman and CoDAs about progress on model to be applied across NC | Samuel Davis | Working on it
| Schedule meeting with CoDA |  | Done
| Send CoDA final survey draft |  | Done
Develop list of districts to partner with on implementation
Rec #101: Assess a defendant’s ability to pay prior to levying any fines and fees | Review Meck bench card, Review Jessie Smith packet for applicability, Work with Jamie Markham to develop model bench card, Work with Jamie Markham to develop model training, Send CoDA final survey draft, Draft and propose new NCSC rule requiring judges to assess ability to pay, Schedule meeting with AOC | Done, Done, Working on it, Working on it, Done | AOC | Reduce use of fines and fees |  |  |  | C2:Judicial | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Review Meck bench card |  | Done
| Review Jessie Smith packet for applicability | Samuel Davis | Done
| Work with Jamie Markham to develop model bench card | Samuel Davis | Working on it
| Work with Jamie Markham to develop model training | Samuel Davis | Working on it
| Send CoDA final survey draft |  | Done
| Draft and propose new NCSC rule requiring judges to assess ability to pay | Samuel Davis
| Schedule meeting with AOC | Samuel Davis
Rec #104: Develop a process to eliminate criminal justice debt | Identify existing processes, current AOC form, Identify and research models in other states, Speak with NCLC about nonlegislative policy options, Define C2 priorities for nonlegislative action - draft memo, GCC Funding pitch, Meet with Laura Holland and Leigh Wicclair about relief and expunction, Draft memo on possible statewide options to expand relief/expunction programs, Draft formal guidance on mass relief opportunities, Send CoDA final survey draft, Research options for one-stop fines/fees owed site | Done, Done, Done, Done, Done, Working on it, Working on it, Done | AOC | Reduce use of fines and fees |  |  |  | C2:Judicial | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Identify existing processes, current AOC form | Samuel Davis | Done
| Identify and research models in other states | Allyson Barkley | Done
| Speak with NCLC about nonlegislative policy options | Samuel Davis, Allyson Barkley | Done
| Define C2 priorities for nonlegislative action - draft memo | Samuel Davis, Allyson Barkley | Done
| GCC Funding pitch | Natalia Botella
| Meet with Laura Holland and Leigh Wicclair about relief and expunction |  | Done
| Draft memo on possible statewide options to expand relief/expunction programs |  | Working on it
| Draft formal guidance on mass relief opportunities |  | Working on it
| Send CoDA final survey draft |  | Done
Research options for one-stop fines/fees owed site
Rec #111: Broaden the use of Advanced Supervised Release | Schedule meeting with CoDA, Send CoDA final survey draft | Done, Done | AOC | [5 empty] | NO
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Schedule meeting with CoDA |  | Done
| Send CoDA final survey draft |  | Done
Rec #112: Eliminate the future use of Violent Habitual Felony Status | Research data on pre- and post-reform of habitual felon status, Structure data request for possible referral to DATA, Schedule meeting with CoDA to discuss future support for legislation, Send CoDA final survey draft, Develop list of districts to partner with on implementation | Working on it, Done, Done, Done | Conference of DAs | Study and revise future sentencing guidelines |  |  |  | C2:Judicial | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research data on pre- and post-reform of habitual felon status | Samuel Davis | Working on it
| Structure data request for possible referral to DATA | Samuel Davis | Done
| Schedule meeting with CoDA to discuss future support for legislation |  | Done
| Send CoDA final survey draft |  | Done
Develop list of districts to partner with on implementation
Rec #113: Eliminate future use of Habitual Felony Status for individuals under the age of 21 or convicted of non-violent drug offenses | Research data on pre- and post-reform of habitual felon status, Structure data request for possible referral to DATA, Schedule meeting with CoDA to discuss future support for legislation, Send CoDA final survey draft, Develop list of districts to partner with on implementation | Working on it, Done, Done, Done | Conference of DAs | Study and revise future sentencing guidelines |  |  |  | C2:Judicial | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research data on pre- and post-reform of habitual felon status | Samuel Davis | Working on it
| Structure data request for possible referral to DATA | Samuel Davis | Done
| Schedule meeting with CoDA to discuss future support for legislation |  | Done
| Send CoDA final survey draft |  | Done
Develop list of districts to partner with on implementation
Rec #114: Amend the habitual felony statute to limit the “look back” period to within 8 years of the charged offense | Research data on pre- and post-reform of habitual felon status, Structure data request for possible referral to DATA, Schedule meeting with CoDA to discuss future support for legislation, Send CoDA final survey draft, Develop list of districts to partner with on implementation | Working on it, Done, Done, Done | Conference of DAs | Study and revise future sentencing guidelines |  |  |  | C2:Judicial | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Research data on pre- and post-reform of habitual felon status | Samuel Davis | Working on it
| Structure data request for possible referral to DATA | Samuel Davis | Done
| Schedule meeting with CoDA to discuss future support for legislation |  | Done
| Send CoDA final survey draft |  | Done
Develop list of districts to partner with on implementation
Rec #116: Review all future sentences after 20 years or before | Draft model policy, Identify models in other states | Working on it, Done | Conference of DAs | Study and revise future sentencing guidelines |  |  |  | C2:Judicial | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Identify models in other states | Allyson Barkley | Done
| Draft model policy | Samuel Davis | Working on it
Rec #118: Establish a truth and reconciliation commission to study North Carolina’s history of criminal justice and race | Identify models, Schedule call with Greensboro TRC to coordinate efforts, Schedule call with Grassroots Law Project, Schedule call with Maryland Lynching Commission, Draft model, Check about ACS | Done, Done, Done, Done, Working on it, Working on it | Victims/Community | Study and revise future sentencing guidelines |  |  |  | C2:Judicial | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Identify models | Samuel Davis | Done
| Schedule call with Greensboro TRC to coordinate efforts | Samuel Davis | Done
| Schedule call with Grassroots Law Project | Samuel Davis | Done
| Schedule call with Maryland Lynching Commission | Samuel Davis | Done
| Draft model | Samuel Davis | Working on it
| Check about ACS | Jasmine McGhee | Working on it
C#3 Legislative Committee
Name | Deliverables | Deliverable Status | Buckets | Solution Section | Check Back In | Resources Needed | Cost | Committee | Issue | Status
Rec #98: Conviction Integrity Unit | Draft memo on CIU models, Call with Leigh Wicclair and Chief Public Defender, Draft plan on NC CIU model | Done, Done, Working on it | [6 empty] | NO
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Draft memo on CIU models |  | Done
| Call with Leigh Wicclair and Chief Public Defender |  | Done
| Draft plan on NC CIU model |  | Working on it
C#4: Local Policy Action Committee
Name | Deliverables | Deliverable Status | Buckets | Solution Section | Check Back In | Resources Needed | Cost | Committee | Issue | Status
Rec #1: Respond more appropriately to situations concerning mental illness, autism, intellectual disabilities, substance abuse, homelessness, and other non-emergency situations | Survey police departments and sheriffs’ offices about existing programs, Analyze results and categorize responders, ARP Funding Discussion, Submission to NC ACC Weekly newsletter | Done, Working on it, Working on it | Grant Makers, Local Government | Reimagine public safety and reinvest in communities |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Survey police departments and sheriffs’ offices about existing programs |  | Done |  |  | 2021-02-23 | 2021-03-06
| Analyze results and categorize responders |  | Working on it |  |  | 2021-03-06 | 2021-03-20
| ARP Funding Discussion |  | Working on it |  |  | 2021-05-25 | 2021-07-13
Submission to NC ACC Weekly newsletter
Rec #3: Fund grassroots organizations that employ promising and peaceful strategies to help communities promote public safety | Identify potential grassroots organizations that promote community-based approaches to public safety, Identify evidence-based approaches to promoting public safety, Submission to NC ACC Weekly newsletter |  | Grant Makers, Local Government | Reimagine public safety and reinvest in communities |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Identify potential grassroots organizations that promote community-based approaches to public safety
Identify evidence-based approaches to promoting public safety
Submission to NC ACC Weekly newsletter
Rec #4: Develop and provide funding to help communities build violence prevention programs | Identify successful community violence prevention programs, GCC funding pitch, Submission to NC ACC Weekly newsletter | Working on it | Grant Makers, Victims/Community | Reimagine public safety and reinvest in communities |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Identify successful community violence prevention programs |  | Working on it
| GCC funding pitch | Natalia Botella
Submission to NC ACC Weekly newsletter
Rec #5: Form local Community Safety and Wellness Task Forces to examine public safety and wellness needs | Identify template for Community safety and Wellness Task Force Development, Attain description and history of Durham's Task Force, Submission to NC ACC Weekly newsletter |  | Victims/Community, Local Government | Reimagine public safety and reinvest in communities |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Identify template for Community safety and Wellness Task Force Development
Attain description and history of Durham's Task Force
Submission to NC ACC Weekly newsletter
Rec #6: Adopt community policing philosophies and plans in collaboration with the communities law enforcement serve | Create a standard definition of community policing, Identify best practices to promote relationship building between LE and communities |  | Victims/Community, Law Enforcement | Strengthen community policing practices |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Create a standard definition of community policing
Identify best practices to promote relationship building between LE and communities
Rec #8: Encourage or require officers to spend non-enforcement time, or live in, the neighborhoods they serve | Collect current examples and success stories of this practice. (including outcome if available), Determine methods for such intervention to be successful |  | Law Enforcement | Strengthen community policing practices |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Collect current examples and success stories of this practice. (including outcome if available)
Determine methods for such intervention to be successful
Rec #9: Publicly acknowledge mistakes by law enforcement to build trust and transparency | Identify models, Examine for legal deterrents |  | Law Enforcement | Strengthen community policing practices |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Identify models
Examine for legal deterrents
Rec #12: Deemphasize felony drug posession arrests for trace quantities under .25 grams | Assemble data to promote positive support of policy change |  | Law Enforcement | Reform investigations |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Assemble data to promote positive support of policy change
Rec #13: Prioritize traffic stops that improve traffic safety | Assemble data to promote positive support of policy change |  | Law Enforcement | Reform investigations |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Assemble data to promote positive support of policy change
Rec #14: Require all consent searches to be based on written, informed consent | Collaborate with LE to identify strengths and weaknesses,, Look at examples elsewhere to begin formulating sample policy |  | Law Enforcement | Reform investigations |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Collaborate with LE to identify strengths and weaknesses,
Look at examples elsewhere to begin formulating sample policy
Rec #16: Establish and expand access to diversion programs | Develop comprehensive inventory of NC Diversion programs, Draft a sample description with budgets, Collect data on effectiveness, Submission to NC ACC Weekly newsletter |  | Local Government | Promote diversion and other alternatives to arrest |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Develop comprehensive inventory of NC Diversion programs
Draft a sample description with budgets
Collect data on effectiveness
Submission to NC ACC Weekly newsletter
Rec #18: Encourage citations and summons in lieu of arrest whenever possible | Identify jurisdiction where this is happening with successful outcomes, Develop evaluation criteria for this policy change |  | Law Enforcement | Promote diversion and other alternatives to arrest |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Identify jurisdiction where this is happening with successful outcomes
Develop evaluation criteria for this policy change
Rec #19: Hire behavioral health professionals in schools | Research and draft memo on positive outcomes of this practice, Define what is "sufficient", Submission to NC ACC Weekly newsletter |  | Local Government, SROs | Revise the role of School Resource Officers |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Research and draft memo on positive outcomes of this practice
Define what is "sufficient"
Submission to NC ACC Weekly newsletter
Rec #20: Fund school personnel training on mental health, first aid, cultural competence/diversity/inclusion, and developmental disability | Collect research on current training practices across the state, Submission to NC ACC Weekly newsletter |  | Local Government, SROs | Revise the role of School Resource Officers |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Collect research on current training practices across the state
Submission to NC ACC Weekly newsletter
Rec #21: Develop inclusive processes for selecting and overseeing SROs | Identify models |  | Victims/Community, Law Enforcement, SROs | Revise the role of School Resource Officers |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Identify models
Rec #61: Establish and fund restorative justice programs in local communities across the state and at various points of the criminal justice system | Inventory of NC programs, GCC funding priority, Submission to NC ACC Weekly newsletter | Working on it | Grant Makers, Victims/Community | Support restorative justice initiatives and victim equity |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Inventory of NC programs |  | Working on it
| GCC funding priority | Natalia Botella
Submission to NC ACC Weekly newsletter
Rec #62: Form a victim advisory group to help develop restorative justice programs and other equity programs for crime victims | Consult with other victim advisory groups to create template |  | Victims/Community | Support restorative justice initiatives and victim equity |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Consult with other victim advisory groups to create template
Rec #71: Deprioritize marijuana-related arrests and prosecution | Research if other DAs (Merriweather, Woodall, etc.) have written de-prioritization policies to use as template |  | Law Enforcement | Decriminalize marijuana possession |  |  |  | C4:Local | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
Research if other DAs (Merriweather, Woodall, etc.) have written de-prioritization policies to use as template
C#5: Communications Committee
Name | Deliverables | Deliverable Status | Buckets | Solution Section | Check Back In | Resources Needed | Cost | Committee | Issue | Status
Rec #61: Establish and fund restorative justice programs in local communities across the state and at various points of the criminal justice system |  |  |  | Support restorative justice initiatives and victim equity |  |  |  | C5:Comms | NO | Working on it
Rec #62: Form a victim advisory group to help develop restorative justice programs and other equity programs for crime victims |  |  |  | Support restorative justice initiatives and victim equity |  |  |  | C5:Comms | NO | Working on it
Rec #65: Recognize racial equity and the rights and perspectives of, and the potential consequences to, harmed parties, survivors, and their families during the justice system process and when any reform is proposed |  |  |  | Support restorative justice initiatives and victim equity |  |  |  | C1:Exec | NO
Rec #97: Establish a Second Look Act to reduce racially disparate sentences through the review and action of those currently incarcerated |  |  |  | Reduce current sentencing and incarceration disparities |  |  |  | C5:Comms | NO | Working on it
Rec #103: Eliminate state government reliance on fines and fees |  |  |  | Reduce use of fines and fees |  |  |  | C5:Comms | NO | Working on it
Rec #117: Prohibit capital punishment for people with serious mental illness and people 21 or younger at the time of the offense and prohibit the use of juvenile adjudications to be considered as aggravating factors |  |  |  | Study and revise future sentencing guidelines |  |  |  | C5:Comms | NO | Working on it
Rec #118: Establish a truth and reconciliation commission to study North Carolina’s history of criminal justice and race |  |  |  | Study and revise future sentencing guidelines |  |  |  | C5:Comms | NO | Working on it
Rec #119: Expand voting rights to those on probation, parole, or post-release supervision for a felony conviction |  |  |  | Reduce collateral consequences of criminal convictions |  |  |  | C5:Comms | NO | Working on it
C#6: Data, Study, and Evaluation Committee
Name | Deliverables | Deliverable Status | Buckets | Solution Section | Check Back In | Resources Needed | Cost | Committee | Issue | Status
Rec #11: Use data and objective criteria, instead of officers' subjective perceptions and beliefs, to drive the level of police presence in neighborhoods | TREC Learning Series: Data, Race, and Policing, Meet with Law Enforcement currently making use of data tools, Propose new recommendation | Working on it, Stuck, Working on it | Law Enforcement | Reform investigations |  |  |  | C6:Data | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| TREC Learning Series: Data, Race, and Policing |  | Working on it
| Meet with Law Enforcement currently making use of data tools |  | Stuck
| Propose new recommendation |  | Working on it
Rec #15: Restrict state law enforcement use of asset forfeiture on low-level seizures where there is no conviction |  |  | Law Enforcement | Reform investigations |  |  |  | C6:Data | Yes | Working on it
Rec #23: Collect data on discipline in schools and school-based referrals to the juvenile courts | Develop plan to present (Gov Office intern) | Done | SROs | Revise the role of School Resource Officers |  |  |  | C6:Data | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Develop plan to present (Gov Office intern) |  | Done |  | C1:Exec
Rec #30: Commission a study on racial disparities in how protests and demonstrations are policed in North Carolina |  |  | Law Enforcement | Peacefully facilitate protests and demonstrations |  |  |  | C6:Data | NO | Working on it
Rec #35: Define and collect use of force data |  |  | Law Enforcement | Revise use of force policies | 2021-06-15 |  |  | C1:Exec | NO | On hold
Rec #53: Collect data on law enforcement recruitment and diversity efforts |  |  | Recruitment | Recruit and retain a racially equitable work force |  |  |  | C6:Data | NO | Working on it
Rec #59: Evaluate law enforcement training programs for effectiveness and desired otucomes | Facilitate conversation with RTI, Add research question for Office of Strategic Partnerships | Working on it, Working on it | Training | Train law enforcement to promote public safety and get community support |  |  |  | C1:Exec | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Facilitate conversation with RTI | Jasmine McGhee | Working on it
| Add research question for Office of Strategic Partnerships | Jasmine McGhee, Ellen Spolar | Working on it
Rec #60: Study the effects of officers' physical and mental health on job performance |  |  | Law Enforcement | Enhance the law enforcement profession |  |  |  | C6:Data | NO | Working on it
Rec #83: Create independent pretrial services and improve data collection | Propose changes to jail data collection, Meet with GDAC to review jail data proposal, Meet with Sheriff Association to float proposed changes/pilot project, Submission to NC ACC Weekly newsletter? | Done, Done, Stuck | AOC | Support restorative justice initiatives and victim equity |  |  |  | C6:Data | NO | Working on it
Subitems | Name | Assigned to | Status | Check Back in Date | Other Comm if App | Timeline - Start | Timeline - End
| Propose changes to jail data collection |  | Done
| Meet with GDAC to review jail data proposal |  | Done
| Meet with Sheriff Association to float proposed changes/pilot project |  | Stuck
| Submission to NC ACC Weekly newsletter? | Greg Sabin
Rec #88: Enhance prosecutors’ data collection, technology, training opportunities, and staffing |  |  | Conference of DAs | Promote racially equitable prosecutorial practices |  |  |  | C6:Data | NO | Working on it
Rec #94: Establish a state commission on the jury system, with an eye towards comprehensive reform |  |  | AOC | Facilitate fair trials |  |  |  | C6:Data | NO | Working on it
Rec 102: Reduce use of fines and fees |  |  | AOC | Reduce use of fines and fees |  |  |  | C6:Data | NO | Working on it
Rec #115: Analyze and report on racial disparities in sentencing laws and recommend possible changes |  |  |  | Study and revise future sentencing guidelines |  |  |  | C6:Data | NO | Working on it
2021-06-15